## Contract Schedule
CONTRACT CHANGE ORDER (AIA G701 STYLE) |  |  | LEGAL CONTRACT
Standard Construction Contract Modification Agreement |  |  | Contract Ref #: AGR-2026-8841
OWNER: Crestwood Hospitality Group LLC AND GENERAL CONTRACTOR: Pinnacle Commercial Builders |  |  | Execution Date: October 30, 2026
CONTRACT RECONCILIATION & SCHEDULE IMPACT
Change Order Number: | CHANGE ORDER #04 (Project: Grandview Hotel Renovation) | Current Change Value: | +$28,450.00 (Structural Steel & Electrical Upgrades)
Original Contract Sum: | $1,450,000.00 USD ¦ Prior Net Change Orders: +$42,800.00 | Contract Time Adjustment: | +14 Calendar Days Added to Substantial Completion Date
Change Item # | Scope Change Description & Justification | Trade Category | Cost Impact ($) | Schedule Impact
CO-4.1 | Architectural Revision: Reinforce Structural Roof I-Beams | Structural Steel | $14,200.00 | +6 Days
CO-4.2 | Upgrade Main Electrical Feeder to 800A for Kitchen Expansion | Electrical | $9,850.00 | +5 Days
CO-4.3 | Additional Drywall Sound Isolation Insulation (STC 55) | Acoustic / Finish | $4,400.00 | +3 Days
LEGAL ENFORCEABILITY & SIGNATURE OF PARTIES: |  |  | Contract Total Value: | REVISED SUM: $1,521,250.00
Execution of this Change Order constitutes full accord and satisfaction for all direct, indirect, and delay costs.
IN WITNESS WHEREOF, the authorized representatives have executed this contract.